## Overview
PyroFinder | Sprint Plan
Project | Real-time fire outbreak detection and monitoring using cameras that already exist at the customer site.
One-Liner | Private property owners suffer from delayed fire awareness; PyroFinder uses existing cameras, YOLO11s fire/smoke detection, and approximate map-based alerts.
Primary Model | YOLO11s; YOLO11n as speed baseline / fallback
Primary Dataset | D-Fire
Primary MVP | Operations & Learning Dashboard + basic Central Control Dashboard; offline polygon-to-map setup for geolocation
Progress Summary
Total Sprints | 9
Done | 0
In Progress | 1
Blocked | 0
Not Started | 8
Completion % | 0%

## Weekly Plan
Meeting | Date | Milestone | Topic | PyroFinder Work Plan | Definition of Done | Owner | Status | Evidence / Link
3 | 2026-05-19 | M1 | Planning, README, GitHub setup | Finalize PROJECT_CONTEXT.md, README.md, Sprint Plan, CLAUDE.md, and repository skeleton. Prepare the 3-minute M1 pitch. | README.md includes all M1 sections; Sprint Plan has measurable weekly DoD; GitHub skeleton exists with app.py, src/, data/, notebooks/, tests/; CLAUDE.md is ready; pitch slides are ready. |  | In Progress
4 | 2026-05-26 |  | Data loading + first Streamlit interface | Prepare D-Fire download/metadata workflow. Build first Operations & Learning Dashboard page for dataset inspection and sample visualization. | Streamlit loads real D-Fire metadata or sample images; at least 20 labeled examples are displayed with fire/smoke boxes; class counts for fire/smoke/background are visible. |  | Not Started
5 | 2026-06-02 | M2 | EDA dashboard + first baseline metric | Build the EDA dashboard for D-Fire and verify supplementary dataset compatibility. Add first baseline metric using YOLO11n on a small reproducible validation subset or documented run. | Dashboard includes at least 3 visualizations: class distribution, bbox count/size distribution, and sample image grid with boxes. Data Card is updated. First YOLO11n baseline metric is calculated or documented. |  | Not Started
6 | 2026-06-09 |  | YOLO11n baseline + evaluation pipeline | Implement model/evaluation wrappers. Run YOLO11n baseline more systematically and save metrics for mAP, precision, recall, F1, false alarm rate, and speed. | Reproducible baseline evaluation exists; metrics are saved to reports/ or shown in the dashboard; inference speed is measured; at least one baseline detection overlay is visible. |  | Not Started
7 | 2026-06-16 |  | YOLO11s main model + inference UI | Fine-tune or load YOLO11s. Compare against YOLO11n. Add uploaded image/video inference with detection overlays and confidence scores. | App accepts uploaded image or short video; YOLO11s detections are shown with fire/smoke boxes and confidence; comparison table documents YOLO11s vs YOLO11n accuracy/speed tradeoff. |  | Not Started
8 | 2026-06-23 | M3 | Published prototype + alert/map flow | Add multi-frame confirmation, alert log, basic camera metadata table, manual image polygon definition, basic polygon-to-map link, and deploy to Streamlit Cloud. | Public Streamlit URL is active; real inference works on sample media; alerts trigger only after N consecutive detections; alert/map prototype is visible; basic tests pass. |  | Not Started
9 | 2026-06-30 |  | UX, mapping setup, and mentor feedback | Improve Central Control Dashboard basics: customer/site/camera map, camera status, mapping status, polygon editing workflow, and alert review. Incorporate mentor feedback. | Dashboard flow is clear: select media/camera, run detection, view alert log, inspect metadata/map, and edit image polygons. At least 3 mentor feedback items are documented and addressed. |  | Not Started
10 | 2026-07-07 |  | Validation, FP/FN review, and tests | Validate with supplementary datasets and FURG video sequences. Add false positive/negative review and tests for data loading, detection wrapper, alert confirmation, and mapping lookup. | Validation results exist for at least one external dataset/video. FP/FN examples are visible. pytest passes. README and Data Card are updated with measured limitations. |  | Not Started
11 | 2026-07-14 | Final | Final demo and defense | Present PyroFinder and defend the problem, data, ML formulation, architecture, risks, limitations, and product value. The final demo now takes place on 14/07 due to schedule constraints. | Stable public demo URL works; final report/presentation are ready; live demo shows data inspection, YOLO11s inference, alert confirmation, mapping output, and metrics/baseline comparison. |  | Not Started

## Exit Criteria
Milestone | Date | Exit Criteria
M1 — Pitch | 2026-05-19 | README / project context complete in GitHub; real dataset selected with URL and Data Card; formal ML problem defined; architecture diagram complete; GitHub skeleton and CLAUDE.md ready; 3-minute pitch prepared.
M2 — Data | 2026-06-02 | Streamlit loads real D-Fire data; dataset inspection and EDA working; at least 3 visualizations; Data Card updated; first YOLO11n baseline metric calculated or documented.
M3 — Published Prototype | 2026-06-23 | Public Streamlit URL active; YOLO11s live inference works; YOLO11s compared against YOLO11n baseline with documented accuracy/speed tradeoff; basic tests pass; alert/map prototype visible.
Final — Demo Day | 2026-07-14 | Documented code; stable public demo URL; final metrics and limitations documented; working end-to-end demo; final presentation/demo defense on 14/07/2026.

## Lists
Status | Priority
Not Started | Low
In Progress | Medium
Blocked | High
Done | Critical